## 0727
DPMDP Implementation and Integration Status
Spalte1 | Implemented | Tested | Integrated | Integrated2 | Tested3 | NPM | Remarks
Body |  |  | - | - |  | -
p1StreamPmData
p1LoadParameters
p1ResolveEsAddress
p1InitKafka
p1UpdateMwdiReplica |  |  |  |  | In progress |  | Query by Thorsten: Check in testing if MWDI ES can be replicated by further consuming applications (e.g. MDOI proxy, etc.)
p1ProcessDevice
p1LoadRawCc
p1FieldsFilter
p1DiscardIrrelevantPmRecords
p1CreateResultCc | [6 empty] | Schema validation failed : Actual equipement / physical propreties / temperature should not be required --> FIXED
p1PrepareTxModes
p1CalculateAiCapacity
p1IterateAiPmSlices
p1CalculateIntervalCapacity
p1RemoveOutOfRangeLevels
p1RemoveDefaultValues
p1IterateEcPmSlices | [6 empty] | no HPD is returned :Utilzation could not be calculated because of missing agregation group
p1CalculateEthernetKpis
p1RemoveDefaultValues
p1CalculateUtilization | [6 empty] | Utilzation could not be calculated because of missing agregation group --> FIX included in DPMDP v1.1
p1RemoveOutOfRangeTemperatures
p1FormattingOutputApt | [6 empty] | Format according tho the schemas
p1FormattingOutputOnf | [6 empty] | Format according tho the schemas
p1TransmittingKafka
p1Storing | [6 empty] | batchtimestamp : need to get it from resultCC instead of having time of execution --> FIXED
p1MaintainDs |  |  |  |  | In progress

## 0724
DPMDP Implementation and Integration Status
| Implemented | Tested | Integrated | Tested | NPM
Body |  |  | - |  | -
p1StreamPmData
p1LoadParameters
p1ResolveEsAddress
p1InitKafka
p1UpdateMwdiReplica
p1ProcessDevice
p1LoadRawCc
p1FieldsFilter
p1DiscardIrrelevantPmRecords
p1CreateResultCc
p1PrepareTxModes
p1CalculateAiCapacity
p1IterateAiPmSlices
p1CalculateIntervalCapacity
p1RemoveOutOfRangeLevels
p1RemoveDefaultValues
p1IterateEcPmSlices
p1CalculateEthernetKpis
p1RemoveDefaultValues
p1CalculateUtilization
p1RemoveOutOfRangeTemperatures
p1FormattingOutputApt
p1FormattingOutputOnf
p1TransmittingKafka
p1Storing
p1MaintainDs

## 0722
DPMDP Implementation and Integration Status
| Implemented | Tested | Integrated | Tested | NPM
Body |  |  | - |  | -
p1StreamPmData
p1LoadParameters
p1ResolveEsAddress
p1InitKafka
p1UpdateMwdiReplica
p1ProcessDevice
p1LoadRawCc
p1FieldsFilter
p1DiscardIrrelevantPmRecords
p1CreateResultCc
p1PrepareTxModes
p1CalculateAiCapacity
p1IterateAiPmSlices
p1CalculateIntervalCapacity
p1RemoveOutOfRangeLevels
p1RemoveDefaultValues
p1IterateEcPmSlices
p1CalculateEthernetKpis
p1RemoveDefaultValues
p1CalculateUtilization
p1RemoveOutOfRangeTemperatures
p1FormattingOutputApt
p1FormattingOutputOnf
p1TransmittingKafka
p1Storing
p1MaintainDs

## 0710
DPMDP Implementation and Integration Status
| Implemented | Tested | Integrated | Tested | NPM
Body |  |  | - |  | -
p1StreamPmData
p1LoadParameters
p1ResolveEsAddress
p1InitKafka
p1UpdateMwdiReplica
p1ProcessDevice
p1LoadRawCc
p1FieldsFilter
p1DiscardIrrelevantPmRecords
p1CreateResultCc
p1PrepareTxModes
p1CalculateAiCapacity
p1IterateAiPmSlices
p1CalculateIntervalCapacity
p1RemoveOutOfRangeLevels
p1RemoveDefaultValues
p1IterateEcPmSlices
p1CalculateEthernetKpis
p1RemoveDefaultValues
p1CalculateUtilization
p1RemoveOutOfRangeTemperatures
p1FormattingOutputApt
p1FormattingOutputOnf
p1TransmittingKafka
p1Storing
p1MaintainDs

## 0626
| Implemented | Tested | NPM | Integrated | Tested
Body |  |  | - | -
p1StreamPmData
p1LoadParameters
p1ResolveEsAddress
p1InitKafka
p1UpdateMwdiReplica
p1ProcessDevice
p1LoadRawCc
p1FieldsFilter
p1DiscardIrrelevantPmRecords
p1CreateResultCc
p1PrepareTxModes
p1CalculateAiCapacity
p1IterateAiPmSlices
p1CalculateIntervalCapacity
p1RemoveOutOfRangeLevels
p1RemoveDefaultValues
p1IterateEcPmSlices
p1CalculateEthernetKpis
p1RemoveDefaultValues
p1CalculateUtilization
p1RemoveOutOfRangeTemperatures
p1FormattingOutputApt
p1FormattingOutputOnf
p1FieldsFilter
p1TransmittingKafka
p1Storing
p1MaintainDs